## Slide 1: Brazosport ISD
Citizens’ Bond Oversight Committee
december 17, 2014

## Slide 2: Welcome
Introductions
  Staff
  Committee Members
  Others

## Slide 3: Charter
Reminder of Committee Purpose
In the interest of time and others, schedule separate meetings to discuss other topics.

## Slide 4: Website Review
www.brazosportisd.net
Comments or Recommendations

## Slide 5: Minutes
Comments, Questions or Changes to the Minutes???
Motion to approve the minutes...

## Slide 6: Project Status
  November 30, 2014 – Total P.O.’s issued – $22,660,982 or 55.72% completed or in progress. Actually paid $21,862,406
  August 31, 2014 – Total P.O.’s issued – $21,970,253 or 54.03% completed or in progress. Actually paid $20,186,203

## Slide 7: Review of Timelines
Project Timelines – See Website
www.brazosportisd.net

## Slide 8: Fall Projects
Classroom Projection/Whiteboard – Finalizing one campus
Roofs – Finalizing B’Wood/B’Port
Gym Floor – B’Wood
Culinary Lab – In progress
Welding and Agricultural Upgrades – Pending Re-allocation
Security Vestibules – Materials Ordered…In progress…need to discuss
Bus Parking – Need to discuss
Others…

## Slide 9: Project Scope
Security Vestibules, Fencing and additional access control at Beutel…
  Vestibule:
    Speaking with Gallagher the storefront material glass already fabricated is $3,800.00. Additional funds needed to continue with project would be $6,675.00 (labor and doors/hardware).
  Badge Readers – Additional needed to make security vestibule functional
    $31,776
  Fencing (rough estimate):
    Option A 1220 L. Ft. $15,567.20 (goes around playground area)
    Option B 1640 L. Ft. $20,926.40 (goes around the entire walking track)
Direction from Committee…

## Slide 10: Re-allocation
Five reallocations…
  TI-INSPIRE – Touchpad – 10/31/14 - $54,725 – approved via email vote - Pulled from “Interactive Whiteboards”
  Bogan Standalone system – 11/20/14 - $20,000 – report only – Pulled from “Wired Network Infrastructure”
  Action Needed:
    Welding Upgrades – 12/17/14 - $300,000 – Action needed – Pull from various curriculum line item
    Bus Parking – 12/17/14 - $185,000 – Action needed – Pull from Ney and Long projects that will be discontinued.

## Slide 11: Re-allocation
Five reallocations (Continued)…
  Action Needed:
    Tracks – $600K each – Action needed – Pull 775K from interactive whiteboards, $100K from Fleming Carpet, $295K from Jane Long roof, 30K from Contingency
      Amount budgeted was for re-surface only – structural issues have been identified
      Worst case scenario has been re-allocated
      Hopper Field Pictures
      Slade Field Pictures
Motion to approve the re-allocations.

## Slide 12: Questions/Discussion/Suggestions
Meeting Schedule
  March 25, 2015
  June 17, 2015
  Sept 16, 2015
  Begin at 5 pm.